## Sheet1
Requirements | Time to complete (Days)
Create Databse for storing points and tag information | 3
Create API for adding datasources, tags and information. Used for admin web app | 5
Create web application for adding and editing location points and associating them with tags | 15
Web Services for handling requests to SQL Server and IP21 | 15
Create Android application | 25
add offline capabilities for storing tag locations and most recent data | 7
provide Sabisu authentication in the application | 5
add QR code scanning | 5
Creation of mongodb database | 2
creation of nodejs web api | 2
pulling of datafrom mongo db to google maps application | 1
creation of tags and putting them into mongodb | 1
ui/css of web app | 1