## Sheet1
Requirements | Time to complete (Days) | Progress | 1 day = ~7/8 hours
Web app
Creation of sql database for location storage | 2 |  | 30/01/2017 - 08/05/2017 | 98
creation of nodejs web api | 2 |  | current total estimate | 49
pulling of datafrom sql to google maps application | 1
creation of locations and putting them into SQL | 1
ui/css of web app | 1
testing of web app | 1
rework of web app | 1
C# web service |  |  | Current Bugs/Issues
Set up ODBC IP21 connection | 2 |  | Web app dropdown box doesn’t change even though the viewmodel value is right
test pulling data from IP21 | 0.2 |  | markers arent actually removed from the map, if the dialog is closed and another point put down in the same place it will create a cluster
rework | 0.8
Set up connection and query handling to SQL | 3
SQL testing | 0.2
rework | 0.8
Android application
Set up of project and acquisition of relevant libraries | 1
adding camera functionality | 0.75
adding GPS/location functionality | 0.75
adding compass - knowledge of direction facing | 2
get data from Node JS web service | 1
creation of non-expanded UI | 2
adding count of items to the UI | 1
creation of expanded UI | 2
adding information from Node JS web service to cards | 1
create details view UI | 1
get data from C# web service | 1
find suitable graphing library | 1
display current data from IP21 | 1
display historical data in graph form | 2
find suitable QR code library | 0.5
integrate QR code library | 1
design QR code data structure | 0.5
read data from QR code | 0.5
open card with data read from QR code | 1
total testing | 5
rework | 7

## Week 1 - Sprint 1
w/c 30/01/2017
tasks | 2017-01-30 | tutor meeting: advice on proposal, notes in proposal document
creation of nodejs web api |  | meeting with Tim B: need to talk to Steve about using Business Framework and coming into Sabisu, reviewed estimates, agreed to meet in either one or two weeks. Also mentioned using a simplified version of anomoly detection
pulling of datafrom sql to google maps application |  | work done: added delete and update functionality to web application, fixed bugs regarding click events, delete dialog added and overlay. Created stored procedures
creation of locations and putting them into SQL |  | to do: tidy up of user interface/look more professional. Tidy up code, remove anything that is redundant. Create test plan. Change cards so they are fixed to location rather than pixel
ui/css of web app
testing of web app | 2017-01-31 | talked to steve about using business framework, he said that it was owned by Sabic and licensed by Sabisu so I wont be able to use it. Also since I wont have access to IP21 it will be better to just have the data stored in SQL
rework of web app |  | Organised a visit to Sabisu for next Wednesday to show progress and get further advice
Project proposal |  | Created test plan for web application, most tests passed but a few bugs were found
Added more CSS and tidyed up code
| 2017-02-01 | Worked on project proposal, need to review project handbook on what to include, include minimum requirements in the deliverables section
need to proof read proposal and fix grammar
Met with Eudes, said to perhaps generalise the app to get it to work with information from the university. Energy levels etc. The app needs to appear useful. Anomoly detection would be very good
| 2017-02-02 | Proof read project proposal and added minimum requirements for each section in deliverables
CSS styling on web app and added jquery toast for instructions
| 2017-02-03 | Project proposal references
| 2017-02-04 | finshed off project proposal

## Week 2
w/c 06/02/2017
| 2017-02-06 | Meeting with Eudes about proposal feedback and tall about getting data
Met with people from the uni to get data for the application. Log in data has potential ethical issues, engery data requires talking to ITACS
Meeting with Tim talked about making the application more generic to work with any database. No longer connecting to IP21
| 2017-02-07 | Proposal rework
web app rework
| 2017-02-08 | went into Sabisu to talk to Steve, said that making the web app more generic would work and is a good idea. He can provide me with some data from Dev Paramop database. Also said I should look into mocking the data myself
proposal hand in
| 2017-02-09 | web app rework
| 2017-02-10 | web app rework
| 2017-02-11 | web app rework, created web service for pulling data about a location
| 2017-02-12 | web app rework, need help getting the bounding box right. +/- 100m from current point

## Week 3
w/c 13/02/2017
| 2017-02-13 | Got the radius from a point working, pulls back all points within 100m
| 2017-02-14 | Testing of web service, started research on Android app
| 2017-02-15 | -
| 2017-02-16 | Initial set up of Android application and installation of Kotlin language
| 2017-02-17 | Camera displays on device and current location is obtained
| 2017-02-18 | trying to resolve issue with using Volley to interact with web services
| 2017-02-19 | -

## week 4
2017-02-20 | Got feedback on proposal, need to be more in depth with the description and make sure that complexity is conveyed
Meeting with Tim to discuss progress so far, mentioned the issue with Volley and I said that I would find someone to help
Given the brief for the project poster
2017-02-21 | Started work on project progress poster
still working on http requests. Volley does work as intended when the app is written in Java. Kolley is a kotlin library to use volley but is currently returning a byte array. Either rewrite the entire app in Java or see if its possible to do the requests in a java class file
2017-02-22 | Got HTTP requests working using kolley and using gson to convert json to java classes
work on project progress poster
2017-02-23 | project poster
started designing UI elements
2017-02-24 | project poster