## Sheet1
Requirements | Time to complete (Days) | Progress | 1 day = ~7/8 hours
Web app
Creation of sql database for location storage | 2 |  | 30/01/2017 - 08/05/2017 | 98
creation of nodejs web api | 2 |  | current total estimate | 49
pulling of datafrom sql to google maps application | 1
creation of locations and putting them into SQL | 1
ui/css of web app | 1
testing of web app | 1
rework of web app | 1
C# web service
Set up ODBC IP21 connection | 2
test pulling data from IP21 | 0.2
rework | 0.8
Set up connection and query handling to SQL | 3
SQL testing | 0.2
rework | 0.8
Android application
Set up of project and acquisition of relevant libraries | 1
adding camera functionality | 0.75
adding GPS/location functionality | 0.75
adding compass - knowledge of direction facing | 2
get data from Node JS web service | 1
creation of non-expanded UI | 2
adding count of items to the UI | 1
creation of expanded UI | 2
adding information from Node JS web service to cards | 1
create details view UI | 1
get data from C# web service | 1
find suitable graphing library | 1
display current data from IP21 | 1
display historical data in graph form | 2
find suitable QR code library | 0.5
integrate QR code library | 1
design QR code data structure | 0.5
read data from QR code | 0.5
open card with data read from QR code | 1
total testing | 5
rework | 7

## Week 1 - Sprint 1
w/c 30/01/2017
tasks | 2017-01-30 | tutor meeting: advice on proposal, notes in proposal document
creation of nodejs web api |  | meeting with Tim B: need to talk to Steve about using Business Framework and coming into Sabisu, reviewed estimates, agreed to meet in either one or two weeks
pulling of datafrom sql to google maps application |  | work done: added delete and update functionality to web application, fixed bugs regarding click events, delete dialog added and overlay. Created stored procedures
creation of locations and putting them into SQL |  | to do: tidy up of user interface/look more professional. Tidy up code, remove anything that is redundant. Create test plan. Change cards so they are fixed to location rather than pixel
ui/css of web app
testing of web app | 2017-01-31 | talked to steve about using business framework, he said that it was owned by Sabic and licensed by Sabisu so I wont be able to use it. Also since I wont have access to IP21 it will be better to just have the data stored in SQL
rework of web app |  | Organised a visit to Sabisu for next Wednesday to show progress and get further advice
Project proposal |  | Created test plan for web application, most tests passed but a few bugs were found
Added more CSS and tidyed up code